The Finnish Children and Youth Foundation

Development of rural schools and communities with solar energy in Ecuador

Revised Project Proposal

June 2010

PROJECT PLAN for years 2009 - 2011

Please note the instructions for filling in this project plan form in the Application guide or the internet: http://global.finland/english/ngo/index.htm

new project

X

continuation of on-going project, MFA  project code_________, project initiation year _______

project is based on earlier forms of co-operation, years_______

the planning of project has been supported by MFA preparation trip allowance, year________

Organisation:

1. Basic information on the Project

| 1.1 Name of organisation registered in Finland | Suomen Lasten ja Nuorten Säätiö Barn- och ungdomsstiftelsen i Finland |
| --- | --- |
| 1.2 Name of Project in Finnish | Aurinkoenergiaa Ecuadorin kouluihin NAPS |
| 1.3 Name of Project in English | Development of rural schools and communities with solar energy in Ecuador |
| 1.4 Name of Project in other relevant language | Desarrollo de escuelas y comunidades rurales con energía solar en Ecuador |
| 1.5 Location of Project (country, province, village/municipality) | Country: Ecuador Province: Chimborazo Counties: Guamote, Colta Province: Bolívar Counties: Guaranda |
| 1.6 Name of the local partner organisation | Fundación Esquel |
| 1.7 Contact details of local partner organisation | República de El Salvador N34-229 y Moscú Edificio San Salvador Oficina 7 y 8 [Quito, Ecuador] Tel: +(5932) 245-3800 Fax: +(5932) 245-3777 Email: programas@esquel.org.ec |
| 1.8 Representatives of the co-operation Partner responsible for the Project and their contact information, if other than above | Cornelio Marchán – Executive President Wilson Andrade – Program Director |
| 1.9 Internet home pages of the co-operation Partner and/or the Project (if any) | http://www.esquel.org.ec/ |
| 1.10 Planned initiation and termination dates (on a yearly level) of the Project | 2009 - 2011 |

Please answer the following question and fill in the budget summary (1.13) only after answering all other questions on the form.

1.11 Summary of the Project plan. Describe here briefly (max. 700 characters) the development problem that this project is addressing, its immediate objective and the practical means through which these objectives are to be reached:

The project has been restructured after the findings made during the diagnostic phase, carried out between late 2009 and early 2010. The main improvements are as follows:

- The scope of the project has been narrowed down in regard to the number of schools involved. In addition, the province of Tungurahua has been left out of the plan. The work in the identified communities will be more intensive.

- The project has clearly been divided into two phases: the installation of solar panels and computers; and the education of teachers in the identified communities to use ICT in their work.

- The employment element has been removed due to two reasons: the principle of streamlining the project and focusing on improving education; and the uncertainty of the projects capability to improve young people’s employment prospects and thus of the added value of the element to the project.

- The improvement of existing electricity networks in the identified communities.

- Part of the project’s funds (181 937,00 €) will be reserved for the continuation of the work, the exact purpose and action plan of which will be defined over the course of the project.

The modifications to the plan are described in detail in the following sections of this proposal.

Changes to summary:

Initially, the summary of the project plan was described as follows:

“The current project seeks to tackle the extreme poverty, underemployment and the high functional illiteracy[1] rates found in the rural counties of the provinces of Chimborazo, Tungurahua and Bolivar. At the same time, these three provinces possess a high percentage of indigenous populations (60%, 15% and 30% respectively), who are one of the most vulnerable members of the population in these provinces as they are the ones who confront the highest levels of poverty and unemployment in their counties. Furthermore, according to statistics from the National Hydrology and Meteorology Institute (INAMHI, acronym in Spanish) of Ecuador, the Highland region, where these provinces are located is characterized by being an area where the solar rays are stronger (due to their high altitude and location near the Equator), where weather conditions seem most favorable for the implementation of solar panels as their precipitation rates are low as well as their vegetation in high altitude counties.

In addition, these three provinces are characterized by having isolated counties and parishes that have low electrification rates. Hence, the project´s immediate objective is to endow centres that offer communitarian interest services located in the provinces of Chimborazo, Tungurahua and Bolivar with solar energy and to ensure a technological transferral that generates/boosts job opportunities for young people. This goal will be reached by the installation of photovoltaic cells in participating communities, by training young people in the maintenance of the solar panels and on the management of the project’s products (which will be chosen after a mapping of the selected areas and meeting with participating local actors is undertaken), such as: the creation of computer labs or centres, the installation of mills and irrigation systems, endowing rural schools with laptops, among others.”

However, based on the results of the diagnosis final report of the Initial Phase, the project was reformulated. The new summary of the project plan is presented as follows:

The current project seeks to contribute to the development of rural schools and communities in the provinces of Chimborazo and Bolívar. Most of the rural communities of the provinces of Chimborazo and Bolívar suffer from frequent and prolonged power cuts that can last up to one week and even months. This situation is due to the distance of the communities from the urban centres, the road access difficulties and geographical conditions that hamper the faster repair of power cuts in the zone. Besides, the communities’ electric systems are usually in bad conditions which is a potential cause of short-circuit and conductors overload. This could be the cause of accidents that put people and goods in danger.

The electric power is shared by the community and normally there is only one electric meter which is located in the school. It is very important for the school and for the community to have permanent electric supply because it enables the accomplishment of the educational program and make the use of didactic, audiovisual and computing resources possible. With electric supply the community members could use in a more efficient way the educational establishments. In this context, the introduction of alternative sources of electricity such as solar energy represents a solution for the power cuts.

The project´s immediate objective is to improve the quality of rural education in the Ecuadorian provinces of Chimborazo and Bolívar. This goal will be reached, through the installation of solar energy systems and safe electrical devices in the selected communities on the one hand, which will guarantee a constant energy supply which will allow the development of educative and social activities. On the other hand, the quality of rural education will be improved by the use of pedagogical applications of Information and Communication Technologies (ICTs) in the classrooms and a training process in the use and maintenance of technological devices (such as computers for instance) and in pedagogical methodologies based on ICTs applications.

1.12 If this Project is the continuation of an earlier project, please describe here the main results of the earlier stages of the Project.

As this project’s aim is to endow participating communities with solar panels in order to improve rural education, it becomes in part, a component of a larger program called “Support for Rural Schools in Ecuador” which Esquel Foundation has developed, since the year 2006 in various phases and in various provinces that confront high poverty levels. In this way, with alternative electrification schemes, the project will boost education quality by providing a constant energy supply, pedagogical applications of ICTs and a training process in the use and maintenance of technological devices. Moreover, with the larger participation of the education community (teachers, education supervisors, parents and students belonging to the community) this project can improve their basic skills and improve the high functional illiteracy rates found in each of the participating provinces.

As the program “Support for Rural Schools in Ecuador” intends to tackle the main problems faced by rural schools, this project becomes a continuation of the previous work in the zone. It reinforces the objective which is the improvement of schools equipment and the pedagogical methodologies.

During the diagnosis Initial Phase and the schools selection process, some of the educational centers of the “Support for Rural Schools in Ecuador” program were taken into consideration, as these schools were having power cuts and the energy supply wasn´t  constant. In this way, the zone of intervention is covered with a larger program and the goal of improving rural education is reached in different perspectives.

1.13 Budget Summary

1.14 Other funding of the Project (if any). If the Project receives other funding, please state here the amount and the source of the funding:

16 763,51 €, see the details in Appendix 7 of the budget form.

2. Local Partner Organisation and nature of co-operation

2.1. Please describe the criteria used in choosing the co-operation Partner.

The Finnish Children and Youth Foundation and Fundación Esquel have cooperated actively since the year 2005. Both integrate the International Youth Foundation´s (IYF) partner network.

The cooperation between FCYF and Esquel started with projects that focused on the improvements of local rural government structures and especially their transparency. The cooperation then moved towards the strengthening of the bilingual education in rural areas.

Esquel has proved to be a reliable expert organization with excellent acceptance among the community organizations and people in the Ecuadorian rural areas.

2.2 Has the Organisation previously worked with this Partner? If so, please describe the nature of this co-operation and when it took place?

The two foundations have earlier carried out the following projects, all with the financial support of the Ministry of Foreign Affairs of Finland:

- 2005-2006: “Local Governance and Participation with Ecuadorian Indigenous and Racially Mixed Populations”;

- 2007-2008: “Strengthening Transparency and Civilian Oversight Mechanisms in Two Local Alternative Governments of Ecuador”;

These two projects contributed to the strengthening of transparency in the local alternative governments (LAGs) in the counties of Nabón and Chordeleg, through empowering the participating indigenous populations to exercise their rights, influence and power within oversight mechanisms.

- 2006-2007: “Support for Rural Schools: Improving the Quality of Education in the Central Highlands in Ecuador”.

This project contributed to the improvement of bilingual education through the further training of indigenous teachers, development of didactic materials and improvement of schools’ infrastructures.

- 2008-2010 (to be finished in September): “Support for Andean Rural Schools: Improving the Quality of Education in the Provinces of Chimborazo and Tungurahua in Ecuador”;

This project is the second phase of the previous project and contributes to the improvement of schools’ infrastructure and equipment, providing furniture and didactic materials, strengthening of the quality of the educational system, promotion and diffusion of Children’s and Adolescents’ Rights and the implementation of an environmental component in the schools’ curricula.

2.3 Additional information on the co-operation Partner.

Esquel is an Ecuadorian non-profit organization that promotes democracy, governance, corporate social responsibility and socio-economic development.  Esquel is known for implementing successful projects on strengthening local governments, building local economies and providing effective social services in the areas of education, culture, the environment, health, migration and social security.

Areas of intervention:

Education:

The objective of this area is to contribute to the improvement of coverage and quality of educational system through the promotion of the learning  and quality education right for excluded population; the strengthening of social context as students, teachers, parents and local institutions; the increase of management quality of educational system.

Migration and development:

The aim of this line of intervention is to create suitable economic and social conditions for development promoting migrants’ rights and refugees, stimulating economic opportunities in the areas more subject to migration and in the communities that receive Colombian refugees; encouraging the creation or the strengthening of institutional services for migrants, refugees and their families.

Local economic development

The intent is to profit of local resources potential in order to expand and diversify the economy, fight poverty and strengthen local private and public actors: the strategy address to the impulse of a territorial management to point to the potential of human and local resources, the dynamism of the economy, the revaluation of culture and protection of the environment. Esquel’s intervention creates income generation and job opportunities direct to the weaker population and stimulate the coordination between actors such as local government, entrepreneur sector, social organization and communities. Within this area of intervention, great efforts are concentrating on boosting sustainable tourism initiatives, promoting the valorization of local resources and the more complete respect and regeneration of the surrounding environment. Esquel has an associate entity, the Corporation for the Development of Micro-enterprises (CODEMIC), which manages Esquel’s micro financial system.

Social responsibility

Esquel involves the participation of the entrepreneur sector as a co-responsible actor of development, together with authorities and citizens, sensitizing to the concept of social responsibility and promoting a suitable institutional environment. Currently Esquel heads the executive secretariat of the Ecuadorian Consortium for Social Responsibility (CERES).

Esquel has worked in 22 of Ecuador’s 24 provinces. At the moment, we have focused our areas of work in the following regions: in the highlands (or Sierra): within the provinces of Chimborazo, Tungurahua, Azuay and Imbabura in the fields of education, migration, local economic development and democratic issues; and within the Northwest of Pichincha, in the fields of education, tourism and local economic development program.

2.4 How will the co-operation Partner participate in the implementation of the Project (e.g. does it provide labour, economic resources, other assets)?

The Esquel Foundation will bear the responsibility for the implementation of the Project in Ecuador. During the initial phase, Esquel worked on the community level and has defined the exact rural sites where the solar panels will be installed. The purpose of the Initial Phase was to carry out a diagnostic work in the rural areas of the Ecuadorian provinces of Chimborazo, Tungurahua and Bolivar, and to carry out any other preparations for the successful implementation of the further phases of the Solar Development project.

For this purpose, Esquel asked IMAGINAR, a expert organization specialized in renewable energies, to carry out a research aimed at identifying schools in the provinces of Tungurahua, Chimborazo and Bolívar, in order to elaborate a baseline and measure the electrification needs in rural schools of the intervention zone. IMAGINAR´s  technical diagnostic of the participating provinces´ rural areas, made recommendations about the schools to be selected, the distance of the communities from the urban centres, the road access difficulties and geographical conditions and the communities’ electric systems, that are usually in bad conditions.

With this information, and with the collaboration of local actors as well as with the help of the Intercultural Bilingual Education Provincial Board of Chimborazo (DIPEIBCH), Tungurahua (DIPEIBT) and that of Bolivar (DIPEIB-B), the criteria for selecting the communities and the beneficiary populations of this project was determined.

In the next phase of the project Esquel will act as coordinator of the planned activities, and will also be in charge of evaluating and monitoring the project’s progress periodically.

In economic terms, Esquel will provide part of the Program Coordinator´s time as well the accountant, the systems and communication’s manager and its training methodology in terms of jumpstarting productive initiatives and schemes. Concerning the beneficiaries, they will participate in the solar panels installation in the selected communities, as well as in the other activities related to the endowment of solar panels: training process in the use and maintenance of technological devices, pedagogical applications of ICTs, among others.  The beneficiaries of the project will participate actively in the training sessions in solar panels management and maintenance. In this way, beneficiaries will generate a sense of ownership and will benefit from the technological transfer throughout the project duration.

2.5 Are there other parties involved in the co-operation (e.g. Finnish, local or international organisations or officials)? If so, please describe their role and involvement in the Project.

A bidding expert will be hired to carry out the bidding competition for selecting the solar panels provider and a solar energy expert will be hired to facilitate in the technical evaluation of the solutions proposed by the bidders.

A volunteering Finnish ICT expert will contribute to the development of the schools’ ICT infrastructure as well as the curricula and teaching methods in the schools.

3. Background and sustainability of the Project

3.1 How was the Project idea initiated? Is it e.g. a part of a larger Program?

The Project idea was initiated in a meeting between the Directors and Presidents/Vice-Presidents of the Finnish Children and Youth Foundation and the Esquel Foundation, as a response to the needs in the rural areas of Ecuador for energy. Esquel and FCYF have cooperated since 2004 in several projects and especially in the projects that supported rural schools the need for energy became evident.

3.2 Describe briefly the environment in which the Project will be implemented.

This project was started with a diagnostic Initial Phase which was implemented from July 2009 to January 2010. Its objective was to carry out a diagnostic work in the rural areas of the Ecuadorian provinces of Chimborazo, Tungurahua and Bolivar, in order to identify the electrification needs of the rural schools in the area.

The implementation of the Initial Phase presented some challenges; the initial objective had to be changed since it was not possible to identify the expected 200 schools without electric energy supply in the provinces of Tungurahua, Chimborazo and Bolívar, as it was defined. Thanks to the secondary data (existent information) provided by the Provincial Directions of the Intercultural Bilingual Education System and the electric companies, we could realize that the initial objective was not feasible. There was only one (1) school identified without electricity and 56 schools that suffer from frequent and prolonged power cuts in two of the three provinces: Bolívar and Chimborazo. For that reason, the objective was reformulated in order to identify at least 100 schools and communitarian centers and the province of Tungurahua was ruled out as an intervention zone. In addition, some of the selected communities to visit were too difficult to access due to the geographical conditions; therefore some of them have been ruled out because the effort of transportation was too big and the short time.

It is important to stress in the fact that even if some selected schools have been ruled out because they were very remote, the selected communities are far from the urban centers and the access roads are in bad conditions. During the Initial Phase, the access difficulties and the distances showed the need to redefine the beneficiaries and the zones of intervention.

For all these reasons, the environment of the project changed during the Initial Phase. Chimborazo and Bolivar provinces are the definitive zones of intervention.

- Chimborazo Province:

The Province of Chimborazo is composed of 10 counties; all have similar characteristics and necessities, with a total territorial extension of 5.999 km2. Riobamba is its provincial capital. This project will work in the the Colta, Pallatanga and Alausí counties.

Demography:

According to the VI National Census of Population and Housing in 2001, the province of Chimborazo registered 403,185 inhabitants, 47.4% men and 52.6 % women. The population is distributed by 39.1% living in urban areas and 60.9% in rural zones. For this reason the territory is considered to have the largest rural and farming population in Ecuador. Around 37% of the total population is indigenous; and 95% of this group exhibits high poverty rates, with a similar rate among men and women.

Economy:

The economy of the Province of Chimborazo is largely based in rural cattle farming, though there are some medium sized companies located near urban centers, but in reduced numbers. The economies of cities and communities are largely characterized by productive artisan practices. Locally produced agricultural products are sold at considerably low prices to intermediaries and there is disorganization among the producers. A high percentage of the population, notably indigenous farmers, has no access to credit from private financial institutions, which affects their economic development.

The climate is predominately temperate and dry, depending on the altitud.

Politics:

Political parties and groups do not exercise much political activity in the counties and rural parishes. In 1997 a change in the Political Constitution of the Republic allowed for the popular election of Parish Board members, increasing the community participation in the political arena.

Culture:

The most commonly used language is Spanish. Most of indigenous persons are bilingual, speaking Quichua as their mother tongue. In the Province of Chimborazo the catholic religion predominates. Churches are important cultural centers in each county.

In the Province of the Chimborazo there are two obvious cultural traditions. One is the mestizo population, which is influenced by the cultural changes of the west. The other is found in the indigenous communities which continue their traditional ways of life; they have not allowed the habits of the consumer society to harm their identity. After an intensive effort, this last group has been able to carry out primary bilingual education efforts, in order to preserve the Kichwa language, while administering teachings based on their own concepts and philosophies. Other traditions may also be observed in the special celebrations of the native populations of Chimborazo, particularly among the Kichwa populations and in the town of Puruhá.  Celebrations are commemorated to remember religious holidays and the traditional character of Pacha Mama (Mother Earth). These events are particularly important during the solstices and equinoxes which are from the 20th to the 23rd of March, June, September and December of every year. They celebrate national holidays, and those religious and cultural ones which are closely tied to their identity. Despite their proximity of one another, each community has certain cultural patterns which make them distinct; these may be seen in food, housing characteristics, traditions, myths and legends, music, and history among others.

Social:

In the rural sector of the Province of the Chimborazo around 85% of the population live below  the poverty line, meaning their family income is smaller than the value of two basic family shopping baskets (USD $604.11 as of August of 2006). In Penipe, 50% of the rural population is living in poverty. The incomes of these families do not cover their basic needs (food/nutrition, health care, education, housing, and social security). National and local government programs are limited in cover and thus are unable to contribute to relieving poverty. In regards to health, an alarming level of the rural population of the province is undernourished (60% of children age 5 and under). The vast majority of the population is in jeopardy of contracting parasites, because of poor sanitary conditions. Nevertheless, preventive health systems, particularly vaccines, have cover up to 80% of the population. The most serious social problem is the lack of job opportunities available in the formal economy, the absence of individual initiatives, and the inability to develop productive projects. This encourages migration of the population to others areas, particularly among younger generations, those between ages of 15 to 29 years old.

- Bolivar Province:

The province of Bolivar is composed of 7 counties, located in the highlands of Ecuador with an extension of 3.926 Km2 (is the smallest province of Ecuador) and an average altitude of 2608m (but some mountains measure till 4500m). Guaranda is its provincial capital. In this project we will help the Guaranda, Chillanes and San Miguel counties.

The climate is particularily variable, passing from the cold and dry to the tropical one. The average temperature is 14 ºC.

Demography:

According to the VI Census of Population and Housing 2001, the Province of Bolivar registered 169,370 inhabitants; 49% men and 51% women. Of the population 74% live in rural areas and of this percentage 35% are 15 years old or younger. Nearly 25% of the total of the population is indigenous, another 68% racially mixed, and 7% is divided between afro-Ecuadorian, white and others.

Economy:

Specialties that distinguish this province are: engraved wooden furniture, guitars, weapons, pyrotechnics, jewelry, batters' production. There are also factories of sweets and candies, fabrics made by loom, sugar cane alcohol distillery and sugar cane production.

Furthermore, 77.6% of the population lives in poverty and the 44% lives in extreme poverty. Out of the indigenous population, 96,8% lives in poverty (98,6% in rural areas) and the 80,9% lives in extreme poverty (83,5% in rural areas).

Culture and Social:

The most commonly used language is Spanish. Most of indigenous persons are bilingual, speaking Ketchua, as their native language. The Province of Bolivar is prevantly of catholic religion, existing a minority of Evangelicalism.

3.3 What is the general state of development in the field of the Project in the area? How does the local government function in this field and in these issues? How does the local government participate in the implementation of the Project - or limit it?

Since this project tackle the energy topic as a fundamental component for human development, the energetic data of Ecuador is necessary to give the general state of the project field and the area of intervention. According to the Latin-American Energy Organization (OLADE) Ecuador has a final energy consumption of 3,61 BOE/hab. According to this data, in 2002, 89,67% of the total electrification was covered; the rural electrification covered only 79,08%.

For the period of 2007-2016, the National Council on Electricity of Ecuador, CONELEC, is taking on a massive program of rural electrification during which it intends to reach rural areas that still don’t count with the service. If possible, it aims to endow them with Non Conventional Renewable Energy. The program seeks to provide electric service where it is more profitable, meaning, where they can serve a greater number of people. This signifies that isolated communities will still remain excluded. The project thus endeavors to provide clean energy to these areas, in order to promote a more equal development for the country.

Thanks to its geographic position, Ecuador benefits from suitable conditions for the installation and the more proper exploitation of photovoltaic cells: this means that a significant investment on solar energy can respond with very good results in terms of quantity of energy generated and stored. The Corporation for the Energetic Investigation on Ecuador is a private non-profit entity that promotes and motivates scientific investigation on renewable energies and energetic efficiency. The Corporation has recently published an atlas of the solar exposure of every square kilometer of Ecuador which will be a crucial tool to establish the more suitable areas to implant the photovoltaic cells.

Furthermore, there are many initiatives at the local level of integration and coordination of social activities, such as the casas comunales and the provision of the service Creciendo con nuestros hijos. These initiatives grow from the civil society and intend to cover necessities of local coordination and social help, as well as organize social recreational moments for the community. But usually these initiatives don’t count with a defined and large budget and they face difficulties even to afford the payment of electricity- necessary in order to provide service after 6 p.m. - or indeed anything that relies on the use of electronic equipment, when available. Endowing these centers with photovoltaic cells will ensure the sustainability and continuity of their activities.

Since an expected result of the project is to improve the rural education making the use of didactic, audiovisual and computing resources possible, it is important to take into consideration connectivity issues in rural areas where the solar panels will be installed. Connectivity is necessary in order to improve computing skills and new teaching methodologies related with the ICTs. For the period 2008-2010, the government is taking a massive program of connectivity as a priority for the national development, in order to assure the access and democratic use of technologies.  In this sense, the project intends to align with the Connectivity National Plan, which is been promoted by the Telecommunications Development Fund (FODETEL).

The project’s implementation can promote the connectivity needs in rural zones as well, creating a communication campaign to spread the project’s experience and raise awareness about the connectivity needs in rural schools.

3.4 How has the Project been planned? Preguntar a FCYF

In July 2009, FCYF and the Esquel Foundation agreed to implement a Diagnostic Initial Phase of the project “Development of rural schools and communities with solar energy in Ecuador”. The Initial Phase’s objective was to identify 200 schools in three provinces: Tungurahua, Chimborazo and Bolívar in order to elaborate a baseline through the application of surveys in 100 of them. The Esquel Foundation asked for IMAGINAR to carry out this diagnostic phase. Before beginning the research, we resorted to secondary data sources in order to confirm the electric coverage situation in the selected provinces. Esquel has accompanied IMAGINAR in the Initial Phase’s process.

The following actions were carried out:

- IMAGINAR compiled information of the National Council of Electrification (Concejo Nacional de Electrificación, CONELEC, in Spanish) about the electric coverage at national level. The National Council of Electrification is the entity that regulates the electric sector in Ecuador.

- Esquel coordinated meetings with the supervisors of the Provincial Directions of the Intercultural Bilingual Education System in the three provinces. Members of Esquel’s technical work team participated to these meetings in order to socialize the project’s content and to introduce IMAGINAR’s representative to the Provincial Directions’ work team. From these meetings, we obtained information about the number of schools and the situation of their electric supply was compiled.

- Members of Esquel’s technical work team together with IMAGINAR’s representative visited the electric companies of Ambato, Riobamba and Guaranda, which are in charge of the electricity marketing in the selected provinces, in order to obtain information about the number of schools with electric supply.

From the meetings with the provincial directions of education, it was determined that practically there are no schools without electricity. Only one school without electricity and 56 schools that suffer from frequent and prolonged power cuts were identified in two of the three provinces: Bolívar and Chimborazo. For that reason, the initial objective was reformulated in order to identify at least 100 schools and communitarian centers.

In October 2009, IMAGINAR was hired to carry out the diagnostic phase based on the new objective. Esquel took part in the coordination of new meetings with the supervisors of the Provincial Directions of the Intercultural Bilingual Education System in the Chimborazo and Bolívar provinces.

The aim of these meetings was to organize the visits to the selected schools in order to determinate their electric needs. In November and December 2009, IMAGINAR visited the selected communities. The access difficulties and the geographical conditions made possible to visit and survey 44 communities. The research calculates the current electric consumption and needs of 140 points, considered among schools and communitarian centers (communal rooms, nurseries, churches, productive centers among others). These points were located in 44 communities that had been visited. A total of 402 buildings were taken into account for the necessary calculations.

Then the Esquel’s technical work team has analyzed the listing of those 44 communities and has prioritized 19 communities from this listing to be considered as the direct beneficiaries of the project.

3.5 Describe the most essential problems of the beneficiaries that the Project is meant to address.

Initially, the description of the most essential problems that the project is meant to address was presented as it follows:

“Direct beneficiaries of this project were the 220 centres that provide services of common interest to the communities. Those centres are settled in communities so isolated that are lacking the electric service or, more often, in communities that are endowed with electricity but that cannot count on the continuity of this service. Moreover, often the communities don’t count with the means to afford the expenditure that those centres require, especially of maintenance and electricity, reducing the capabilities of those centres to provide their services. The installation of solar panels will solve those problems by providing a stable source of electricity, which only costs for the community will be those referred to maintenance.

Others beneficiaries of the project are the youngsters living in the communities where local authorities and grassroot associations will decide to install the solar panels. In these provinces, in rural areas, the underemployment has an average of 88% and for young people there are not so many job possibilities. The project aims to offer to a selected group of young people a professional training for the maintenance of the equipment installed as well as the solar panels. The idea is to offer them the possibility of a paid job in the same communities where they have born and grown”.

However, the diagnosis final report of the Initial Phase gave us a more detailed and realistic description of the essential problems that the project’s beneficiaries are going through:

The selected communities suffer from frequent and prolonged power cuts that can last up to one week and even months. This situation is due to the distance of the communities from the urban centres, the road access difficulties and geographical conditions that hamper the faster repair of power cuts in the zone. Besides, most of the time the communities’ electric systems are in bad conditions which is a potential cause of short-circuit and conductors overload. This could be the cause of accidents that put people and goods in danger. Selected schools and communities also have a very low charge of power.

The electric power is shared by the community and normally there is only one electric meter which is located in the school. It is very important for the school and for the community to have permanent electric supply because it enables the accomplishment of the educational program and make the use of didactic, audiovisual and computing resources possible. With electric supply the community members could use in a more efficient way the educational establishments. In this context, the introduction of alternative sources of electricity such as solar energy represents a solution for the power cuts.

Furthermore, rural schools’ current needs in equipment are very important. Their current needs in equipment are specially focused on lighting and computers. The project plans to provide rural schools of the selected communities with computers to improve the students and teachers’ technological skills and introduce new teaching methodologies based on ICTs applications.

3.6 What are the risks that can compromise the outcome of the Project? How is the Project organisation planning to minimize these risks?

The potential risks that may generate drawbacks in the development of the project may include: 

First, we must take into consideration that the lack of political and economic stability in the country could represent a problem that may produce a delay in the normal development of the project activities. For instance, political changes may influence the education authorities' support for the project's activities.

At the moment, Ecuador has accomplished a democratic process and new elected authorities are starting their functions.  However, the country continues living law changes and reforms. Such reforms can be binding and can consequently lead to amend the content of the trainings and workshops envisioned for this project; for which Esquel Foundation, will carry out the adjustments that are required in this regard in order to conform to the reality.

Weather conditions may generate an important drawback in the project activities because this can make the access to communities very difficult or even impossible. The Initial Phase report shows the road conditions and the difficulties caused by the weather; we find suggestions in order to make possible the work with remote rural schools. In this sense, schools selection has been made taking into consideration these risks.

Moreover, it is possible that communities, once the panels and the additional equipment have been installed, don’t use the providing benefits. In order to avoid this possibility, the project has previewed a training process in solar panels management and maintenance. During this training process, the participants will get familiar with the solar panels and will develop a sense of ownership in order to take advantage of new technological tools.

Finally, it is important to consider that the lack of economic stability produces prices changes and this could hamper the purchase of equipment materials.

3.7 Will the Project create a new institution or procedure or is it going to support some existing structure?

The current project will not create a new institution or procedure. This project is part of a larger program called “Support for Rural Schools in Ecuador” which Esquel Foundation has developed, since the year 2006, in various provinces that confront high poverty levels. Indeed, the project will provide rural schools with solar panels in order to guarantee a constant electric energy supply that allows the permanent development of teaching activities in the classrooms. Moreover, by introducing new teaching methodologies based on ICTs applications, the project seeks to improve the quality of education in the selected schools.

3.8 How and when will the responsibility of the Project be transferred to the local government, local organisation or to the beneficiaries?

Infrastructure and Materials

Those responsible for the execution of the project are Esquel Foundation, jointly with the local actors such as community leaders, provincial board of the Intercultural bilingual education system, community based organizations. Concerning the endowment of solar panels, selected communities will be the legal owners of them at the end of the project.

Social and Cultural

Regarding all the trainings, they will take into consideration all the social and cultural conditions of each location. After the project has built the capacity of the teachers, students and the larger community in the use and maintenance of solar panels as well as the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications, community members will have the responsibility of promoting their knowledge and disseminate the project to the local communities.

After the workshops in each community to raise awareness about the solar panel benefits and create a communitarian sense of ownership of this technological tool, teachers and community members will have the responsibility of raising awareness about energy schemes and their economic and cultural benefits.

Financing

Esquel Foundation, the Provincial Boards of Intercultural Bilingual Education and the selected communities will contribute with in-kind counterparts such as locations for meetings and maintenance of the solar panels that are placed in their schools.

The community will support with the maintenance of the entire infrastructure provided.  Esquel will carry out post-project follow-ups, with its own or foreign resources, in order to assure that the communities, their common interest centres and the school zones endowed with solar panels and additional products of the technological transferal continue to benefit from the project.

On the other hand, Esquel Foundation, which is continuously working in the region, will place emphasis in developing a strong social network that will be felt throughout the project so that the common interest centers become reference points of alternative and renewable energy of their communities.

4. Beneficiaries

4.1 Who are the direct beneficiaries of the Project? How many are they (approx.)?

Initially, it has been estimated that the project will install 50 solar panels during the first year. During the second year, the project would be extended to the province of Bolivar, where a total of 70 panels will be installed in the three provinces. Finally, it was expected that during the third year the project will install a total of 100 panels in the three provinces, the exact location of which will depend on the decisions taken during the participatory meetings. In total, 220 centres were estimated to benefit from the solar panels installation. In addition, the project targeted 120 young people as beneficiaries belonging to the participating communities that would benefit from a professional training that will allow them to access to an income-generating job in the same rural area where they live.

After the Diagnosis phase of the project has been implemented and the centres that will benefit from the installation of solar panels have been selected, we can define the real number of direct beneficiaries.

The diagnostic work in the rural areas of the Ecuadorian provinces of Chimborazo, Tungurahua and Bolívar showed the electrification needs of the rural schools and communitarian centres in the area. The main outcomes of these process showed that the level of electric coverage in the selected provinces is very high: Tungurahua 95-99%, Chimborazo 95-99%, Bolívar 90-95%. There is only one school without electric energy in the three provinces. Besides, according to the supervisors of the Intercultural Bilingual Education centres, there are 57 schools with constant power cuts in the Chimborazo and Bolívar provinces. Consequently, it was not possible to identify 200 schools without electricity as it was scheduled by the initial objective.

As the electric coverage in the initial zones was very high, the project´s intervention changed: only the provinces of Chimborazo and Bolívar.  A baseline for provinces of Chimborazo and Bolívar has been created and some diagnostic report´s recommendations regarding the next steps for the project’s implementation has been elaborated. Following these recommendations, 19 communities have been selected in the provinces of Chimborazo and Bolívar to benefit from the solar panels installation. A total of 81 panels are required to cover the energy needs of these communities. 1504 students and 93 teachers will be the direct beneficiaries of the project. (See the Schools selection document – appendix 1)

Moreover, with the Initial Phase diagnostic report´s recommendations the expected results changed. The professional training for young people in order to allow them to access to an income-generating job has been changed. The project now focuses on the improvement of rural education by the use of pedagogical applications of ICTs in the classrooms and a training process in the use and maintenance of technological devices.

4.2. Who are the indirect beneficiaries of the Project?

The indirect beneficiaries of the project are students’ parents and in general families belonging to the selected communities where the project will work.  As there have been changes in the selection of the project’s direct beneficiaries, the indirect beneficiaries are:

Chimborazo province:

Guamote and Colta counties: 1098 families

Bolivar province:

Guaranda county: 742 families

For a total of 1840 rural families in the provinces of Chimborazo and Bolívar provinces

4.4 Define the nature of participation in the Project by each group of beneficiaries.

The new direct beneficiaries of the project (after the diagnostic work) are students and teachers from 19 educational centres belonging to the Intercultural Bilingual Education system in the rural zones of Bolívar and Chimborazo provinces. These schools will receive solar panels and computers according to their power needs.

First of all, the nature of the participation of all direct beneficiaries will be that of providing inputs, ideas, knowledge, points of view and most of all, deciding on the following activities:

- Meetings with the parish boards representatives (Juntas Parroquiales), teachers, the community leaders, provincial board of the Intercultural bilingual education system, community based organizations, among others to: socialize the project objectives and define where to install the panels. During this activity, the division of responsibilities and counterparts will be chosen.

- Meetings with community leaders, provincial board of the Intercultural bilingual education system, in order to define the practical applications of ICTs to be implemented in the educational field based on the diagnosis report.

In addition, the beneficiaries will receive a training process in solar panels management and maintenance, as well as workshops to raise awareness about the solar panel benefits and create a communitarian sense of ownership of this technological tool. In the future, beneficiaries will be owners and responsible of the maintenance of the equipments.

As the Initial Phase report revealed the necessity of improve the selected communities' electrical devices, project beneficiaries will participate actively in this new activity identified after the diagnosis phase of the project.

5. Objective, plan of action, monitoring and information

Objectives

5.1 What is the long-term development objective of the Project?

To provide solar energy system in order to improve the rural education in the Ecuadorian provinces of Chimborazo and Bolívar.

5.2 What is the direct objective of the Project? (Limited by the area of implementation and the group of beneficiaries)

To improve the quality of rural education through a constant energy supply, pedagogical applications of ICTs and a training process in the use and maintenance of technological devices, in the Ecuadorian provinces of Chimborazo and Bolívar.

5.3. What are the results targeted by this Project?

The project will have two main results, as follows:

Result 1: Communitarian centres (schools, communal rooms and others) count with solar energy and safe electrical devices to guarantee a constant energy supply which allows the development of educative and social activities.

Result 2: The quality of rural education has been improved by the use of pedagogical applications of ICTs in the classrooms and a training process in the use and maintenance of technological devices.

Result 3: A needs assessment for the proceedings of the project will be carried out simultaneously with the implementations of Results 1 and 2, and a new component will be added to the project plan after the needs assessment has been completed. A total of 181 937 € is reserved for this the development and implementation of the new component. The sum is allocated Appendix 3 (Materials, procurements and investments) for year 2011

Implementation

5.4 Describe the activities by which the results and immediate objectives are to be accomplished. If possible, please also give a rough timetable (by year) of project implementation.

Result 1:

A1. Carry out a technical diagnosis to identify the electrification needs of rural communities in the provinces of Chimborazo, Tungurahua and Bolívar, in order to select the communities which will benefit from the solar energy system.

A2. Meetings to be held with local actors such as: the parish boards representatives (Juntas Parroquiales), the community leaders, provincial board of the Intercultural bilingual education system, community based organizations, among others to: socialize the project objectives and define where to install the panels.

A3. Improvement of the selected communities’ electrical devices to guarantee safety minimum standards.

A4. Delivery of the solar panels by the provider in the selected communities.

A5. Installation of solar panels by the provider in the selected communities.

A6. To select a group in each community and carry out a training process in solar panels management and maintenance by the provider.

A7. To sign the delivery certificate that assures the legal transference of the solar panels property with the community representatives.

A8. To carry out a workshop in each community to raise awareness about the solar panels benefits and create a communitarian sense of ownership of this technological tool.

Result 2:

A1. To carry out a diagnosis report about the possible applications of ICTs in the educational field.

A2. Meetings with local actors such as: the community leaders, provincial board of the Intercultural bilingual education system, in order to define the practical applications of ICTs to be implemented in the educational field based on the diagnosis report.

A3. To provide rural schools of the selected communities with computers to improve their technological skills and introduce new teaching methodologies.

A4. To carry out a training process to the schools' teachers in the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications.

A5. To systematize the experience and knowledge that the project has produced.

A6. To elaborate a communication plan in order to spread the experience and knowledge that the project has produced among local authorities.

A7. To implement the communication plan among local authorities.

Result 3:

A1. Needs assessment for the proceedings will be carried out.

A2. The activities related to the new component will be carried out.

The project also previews a “zero” result that includes all the jumpstarting activities as well as the closing of the project, as follows:

R0.A1. Elaboration of the operative plan of the project.

R0.A2. Implementation of the Planning, Monitoring and Evaluation System (SPME-acronym in Spanish) of the Esquel Foundation.

R0.A3. Implementation of the closing process of the project.

FCYF will support Esquel with the following activities:

- Relating to R.1.A4 y A5, FCYF will hire a consultant to carry out the bidding competition in order to select the solar panels provider and in making the contract. A solar panels expert may be hired if a need to evaluate the quality of the products offered occurs. FCYF will sub-contract the solar panels provider to deliver and install the panels to the selected sites.

- Relating to R.2.A1-A4, a Finnish volunteering ICT expert will support Esquel in defining the ICT and education needs in the Intercultural bilingual education system.

5.6 Describe the implementation and monitoring organisation of the Project and the responsibility of each party therein.

Structure of the implementation and monitoring organization of the Project:

The project’s coordinator is responsible for the organization of the implementation of the project. The project’s coordinator usually works under the Programs and Cooperation General Coordinator’s authority as most of the Esquel’s projects are part of larger programs and processes.

All the projects implemented by Esquel are monitored and analyzed through the Planning, Monitoring and Evaluation System developed by the Foundation. Then the viability of the project is evaluated by the Administrative and Financial Department. The monitoring system, which consists of an internal quarterly evaluation, allows for problems within the project to be corrected during its implementation, such as drawback corrections, measuring the degree of compliance of the project’s goals and indicators while the project is implemented.

Finally, all the implementation and monitoring processes held in the implementation of each project are supervised and evaluated by the Programs and Cooperation General Coordinator, the Monitoring Coordinator, the Quality Coordinator and members of the staff that work in these departments, which supervise that each project is run and implemented under the compliances needed to be kept with the ISO 9001:2008 that Esquel has attained since the year 2006.

In the specific case of this proposal, its implementation will be defined by the project’s coordinator together with the participation of local actors and direct stakeholders of the project. Hence, through the implementation of the project’s first activities (a technical diagnosis identifying the electrification needs of rural communities in the provinces of Chimborazo, Tungurahua and Bolívar, in order to select the communities which will benefit from the solar energy system) the exact locations to place solar panels will be defined as well as the needs of the direct beneficiaries of the project will be understood and tackled by the project. After this is done, the project’s coordinator will plan the rest of activities according to the timeline envisioned by the project.

Moreover, the coordinator of the project will have to:

-  Define the terms of reference for inter-institutional Agreements to be made as well as to hire professional staff needed for the execution of the project, together with the Programs and Cooperation General Coordinator.

- Elaborate and update the projects’ information database and its continuous systematization following the guidelines of the established monitoring and evaluation process created by Esquel entitled the Planning, Monitoring and Evaluation System (SPME, acronym en Spanish).

- Provide orientation and assistance in elaborating the pertinent follow-up schemes to work plans and activity time-lines for the execution of the project.

- Resolve problems pertaining to the fulfillment of the project’s objectives.

- Elaborate regular follow-up reports about the progress and compliance of the project’s objectives and present them to the Programs and Cooperation General Coordinator.

Programs and Cooperation General Coordinator:

The Programs and Cooperation General Coordinator is in charge of overseeing Esquel’s various programs. He is charged of maintaining the efficiency and effectiveness of each program by working with coordinators and local supervisors. For the duration of this project, he will work together with the project’s coordinator and use feedback to monitor the project’s progress and resolve any problems that may arise.

Monitoring Coordinator:

This coordinator is in charge of the Planning, Monitoring and Evaluation System designed by Esquel during the year 2001. This integrated system supports a culture based on permanent learning, where constant feedback is implemented into the processes with the help of the project’s beneficiaries.

Financial Management:

Esquel Foundation counts on its staff of experienced accountants and financial experts to guarantee the monetarily sound operation of each of the Foundation’s projects.

5.7 How do the responsible persons of the Finnish organisation follow the implementation of the Project and the use of financial resources? How do they participate in its implementation?

FCYF holds an overall responsibility of the project implementation. The main people in charge of the project management in FCYF are the development manager and the development cooperation coordinator.

On the basis of the project agreement funding will be released only after the review and approval of the narrative and financial reports which will be submitted by Esquel to FCYF twice a year. Esquel will also be in regular e-mail (and telephone) contact with Esquel through exchanging information about the project, its implementation and progress. In addition FCYF will carry out a project monitoring trip once a year.

5.8 How do the local co-operation Partners follow the implementation of the Project and the use of financial resources?

During the implementation of the project Esquel will coordinates and executes the planned activities. The project’s coordinator or his/her assistant will visit the project at least four times a month; they must monitor and evaluate the fulfillment of the activities related to the deadlines.

Monitoring activities of the Project’s Coordinator:

- Maintain direct relations with the Programs and Cooperation General Coordinator as well as with the Administrative and Financial Direction in defining the general guidelines of the project, alliances, strategies for monitoring and evaluating the course of the project, the completion of budgets and financial and administrative processes.

- Elaborate and update the projects’ information database and its continuous systematization following the guidelines of the established monitoring and evaluation process created by Esquel entitled the Planning, Monitoring and Evaluation System (SPME, acronym in Spanish).

- Maintain permanent communication with the project coordinating team as well as with the Programs and Cooperation General Coordinator and the Financial and Administrative Direction. The on-site coordinator is required to participate in all departmental and institutional coordination meetings to which he/she is invited.

- Elaborate regular follow-up reports about the progress and fulfillment of the project’s objectives and present them to the Programs and Cooperation General Coordinator.

Monitoring activities of the Programs and Cooperation General Coordinator:

For the duration of this project, he will work jointly with the project’s coordinator and use feedback to monitor the project’s progress and resolve any problems that may arise. The General Coordinator will visit the project three times a year.

Monitoring activities of the Monitoring Coordinator:

He will implement the Planning, Monitoring and Evaluation System for this project and especially its monitoring component. The Monitoring component is a permanent observation and documentation process of the project’s information. The tool used for this purpose is the Annual Operative Plan, designed with the aforementioned methodology. This monitoring strategy delivers continuous and structured information that provides feedback on: the progress made in each project or program, the conditions of the expected results and the external changes that may influence the project’s execution or implementation. The monitoring component helps adjust institutional actions to a dynamic reality, while maintaining the project’s progress.

Esquel’s External audit:

Furthermore, as the Planning, Monitoring and Evaluation System only provides the monitoring of the activities of the project, Esquel also carries out an external audit with a recognized firm, on all the projects undertaken by the Foundation throughout the year.

5.9 What kind of numerical or other data will be collected on the advancement of the Project?

The advancement of the project will be measured by the following indicators:

Indicators of the Direct Objective:

- All the selected communities count with a constant energy supply at the end of the project.

- Selected schools' teachers have been trained in the use of pedagogical applications of ICTs in the classrooms and in the use and maintenance of technological devices, at the end of the project.

- At the end of the project, a communication plan has been implemented in order to spread the project's experience among local authorities.

Indicators of the result 1:

- A technical diagnosis that identifies the electrification needs of the selected rural communities has been carried out in the first year of the project implementation.

- All the selected communities count with improved electrical devices at the end of the project.

- All the selected communities count with photovoltaic cells at the end of the project.

Indicators of the result 2:

- A diagnosis report about the possible applications of ICTs in the educational field has been carried out at the end of the project.

- At the end of the project, the selected communities count with at least 1 computer in the classroom.

- Teachers of the selected schools have been trained in the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications.

- At the end of the project, a communication plan has been implemented in order to spread the project's experience among local authorities.

5.10 Where and how will the accounting and audit of the Project be arranged?

Regarding the project’s implementation in Ecuador, the project’s accounting is carried out by the Esquel Foundation, with our accounting system called “Solomon”. This accounting system presents accounting modules for each of the projects we have, and also uses approved budgetary items. The costs incurred in Finland will be accounted by FCYF. The payments to Esquel will be entered as obligations in FCYF’s financial statement.

Every year, Esquel also carries out an external financial audit with a recognized firm, on all the projects undertaken by the Foundation throughout the year. FCYF’s auditor, PricewaterhouseCoopers, will audit the Finnish accounts for both the project and the Foundation in general.

In order to establish quality standards necessary for planning and conducting audits, reporting results and taking actions that involve continuous improvement of its processes, Esquel has implemented a Quality Management System, according to quality standards of the ISO 9001:2008.

The following table presents the entities that will be responsible for carrying out the financial audit and the Quality Management Audit:

| Type | Evaluator | Period of Control |
| --- | --- | --- |
| Financial Audit | INTERNATIONAL DELOITTE & TOUCHE | Annual |
| Quality Management Audit | INTERNATIONAL COTECNA QUALITY RESOURCES - ECUADOR | Semi-annually |

In addition, Esquel will hire the services of a firm that will specifically carry out the financial audit of this project.

5.11 Will the organisation evaluate the Project during its implementation or afterwards? If the answer is yes, please describe how it will be carried out.

Esquel conducts quarterly monitoring evaluations in order to assess the degree of progress within all of its projects to know whether there are drawbacks in the implementation, where the necessary corrective actions are taken.

On the other hand, internal biannual monitoring assessments are conducted by Esquel to analyze the degree of compliance of the goals and indicators of the projects under implementation.

Furthermore, Esquel conducts internal reports on a quarterly basis and Process Reports for all financial supporters and program partners every six months, unless otherwise directed.

Process Reports will include information organized in the following format: (1) Summary; (2) Activities Carried Out; (3) Problems Found and Solutions Taken; (4) Lessons Learned; (5) Unexpected Results; (6) Conclusion.

Finally, at the end of the project, a systematization report on the results of the project will be presented.

Planning, Monitoring and Evaluation System

The project will implement the Planning, Monitoring and Evaluation System (PMES), which was designed by Esquel in the year 2001. This integrated system supports a culture based on permanent learning, where constant feedback is implemented into the processes with the help of the project’s beneficiaries.

The Planning component is based on our unified institutional methodology of planning by results. The methodology is our own adaptation of the ZOPP (Planning system based on objectives) of the GTZ; a revised Logical Framework Approach and other methodological contributions. The planning component is based on a system of indicators that facilitate effective monitoring and evaluation processes.

The Monitoring component is a permanent observation and documentation process of the project’s information. The tool used for this purpose is the Annual Operative Plan, designed with the aforementioned methodology. This monitoring strategy delivers continuous and structured information that provides feedback on: the progress made in each project or program, the conditions of the expected results and the external changes that may influence the project’s execution or implementation. The monitoring component helps adjust institutional actions to a dynamic reality, while maintaining the project’s progress.

The Evaluation component is also a continuous learning process used to strengthen and improve projects, incorporate multiple intervention approaches, focus towards real and relevant issues, promote participation and flexibility and, perhaps most importantly, build internal capacities.

5.12 Describe how the organisation will inform about the Project. Give details on the goals, target groups, information material and information channels.

FCYF will update its communication strategy in 2010. The strategy will define the objectives and means of the foundation’s development cooperation communication. The foundation will intensify its efforts in increasing the awareness of its development cooperation work among the key stakeholders and the general public.

FCYF will inform its stakeholders and the Finnish in general about the project, about its execution, its outcomes and significance to the sustainable development efforts in Ecuador through the following media:

- Internet: FCYF’s homepage (www.slns.org, to be updated in early 2011), e-Newsletters, linked homepages of FCYF’s national and international partners.

- Printed media

- Seminars, conferences and workshops (either organized or attended by FCYF)

6. Free-form description of the Project and its operation (optional: if the other questions in this form are not suitable or sufficient to describe the Project, please use this space to give additional information)

LOGICAL FRAMEWORK/Esquel

| DESCRIPTION | INDICATORS | MEANS OF VERIFICATION | RISKS |
| --- | --- | --- | --- |
| LONG TERM OBJECTIVE |  |  |  |
| L.T.O. To provide solar energy systems in order to improve the rural education in the Ecuadorian provinces of Chimborazo and Bolívar. |  |  |  |
| DIRECT OBJECTIVE |  |  |  |
| D.O. To improve the quality of rural education through a constant energy supply, pedagogical applications of ICTs and a training process in the use and maintenance of technological devices, in the Ecuadorian provinces of Chimborazo and Bolívar. | All the selected communities count with a constant energy supply at the end of the project. Selected schools' teachers have been trained in the use of pedagogical applications of ICTs in the classrooms and in the use and maintenance of technological devices, at the end of the project. At the end of the project, a communication plan has been implemented in order to spread the project's experience among local authorities. | Every three months reports of the photovoltaic cells operation. Attendance records. Training final report. Participants' polls. Pictures. Project's reports. Communication plan document. Pictures. Project's reports. | Lack of political and economic stability in the country. Political changes may influence the education authorities' support for the project's activities. |
| RESULTS |  |  |  |
| R.1. Communitarian centers (schools, communal rooms and others) count with solar energy and safe electrical devices to guarantee a constant energy supply which allows the development of educative and social activities. | A technical diagnosis that identifies the electrification needs of the selected rural communities has been carried out in the first year of the project implementation. All the selected communities count with improved electrical devices at the end of the project. All the selected communities count with photovoltaic cells at the end of the project. | Technical diagnosis report. Project's reports. Pictures. Certification of receipts. Project's reports. Pictures. Certification of receipts. Project's reports. | Weather conditions don't allow the access to communities. Lack of economic stability produces prices changes that hamper the purchase of equipment materials. |
| R.2. The quality of rural education has been improved by the use of pedagogical applications of ICTs in the classrooms and a training process in the use and maintenance of technological devices. | A diagnosis report about the possible applications of ICTs in the educational field has been carried out at the end of the project.At the end of the project, the selected communities count with at least 1 computer in the classroom. Teachers of the selected schools have been trained in the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications. At the end of the project, a communication plan has been implemented in order to spread the project's experience among local authorities. | Diagnosis report.Project's reports.Certification of receipts.Pictures.Project's reports.Attendance records.Training final report.Participants' polls.Pictures.Project's reports.Communication plan document.Pictures.Project's reports. | Lack of economic stability produces prices changes that hamper the purchase of equipment materials. Teachers are not willing to implement in their classrooms what they learned during the trainings. |
| ACTIVITIES |  |  |  |
| RESULT 1 |  |  |  |
| R.1.A1 Meetings to be held with local actors such as: the parish boards representatives (Juntas Parroquiales), the community leaders, provincial board of the Intercultural bilingual education system, community based organizations, among others to: socialize the project objectives and define where to install the panels. |  |  |  |
| R.1.A2 Improvement of the selected communities' electrical devices to guarantee safety minimum standards |  |  |  |
| R.1.A3 Delivery of the solar panels by the provider in the selected communities |  |  |  |
| R.1.A4 Installation of solar panels by the provider in the selected communities |  |  |  |
| R.1.A5 To select a group in each community and carry out a training process in solar panels management and maintenance by the provider. |  |  |  |
| R.1. A6 To sign the delivery certificate that assures the legal transference of the solar panels property with the community representatives |  |  |  |
| R.1.A7 To carry out a workshop in each community to raise awareness about the solar panel benefits and create a communitarian sense of ownership of this technological tool. |  |  |  |
| RESULT 2 |  |  |  |
| R2.A1 To carry out a diagnosis report about the possible applications of ICTs in the educational field. |  |  |  |
| R2.A2 Meetings with local actors such as: the community leaders, provincial board of the Intercultural bilingual education system, in order to define the practical applications of ICTs to be implemented in the educational field based on the diagnosis report. |  |  |  |
| R2.A3 To provide rural schools of the selected communities with computers to improve their technological skills and introduce new teaching methodologies. |  |  |  |
| R2.A4 To carry out a training process to the schools' teachers in the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications. |  |  |  |
| R.2.A5. To systematize the experience and knowledge that the project has produced. |  |  |  |
| R.2.A6. To elaborate a communication plan in order to spread the experience and knowledge that the project has produced among local authorities. |  |  |  |
| R.2.A7. To implement the communication plan among local authorities. |  |  |  |
| R.0.A.1 Elaboration of the operative plan of the project |  |  |  |
| R.0.A.2 Implementation of the Planning, Monitoring and Evaluation System (SPME-acronym in Spanish) of the Esquel Foundation. |  |  |  |
| R.0.A.3 Implementation of the closing process of the project. |  |  |  |

| TIMETABLE OF ACTIVITIES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| ACTIVITIES | MONTHS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |
| R.0. Project's management process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.0.A.1 Elaboration of the operative plan of the project | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.0.A.2 Implementation of the Planning, Monitoring and Evaluation System (SPME-acronym in Spanish) of the Esquel Foundation. | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x | x |
| R.0.A.3 Implementation of the closing process of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |
| R.1. Communitarian centers (schools, communal rooms and others) count with solar energy and safe electrical devices to guarantee a constant energy supply which allows the development of educative and social activities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A1 Meetings to be held with local actors such as: the parish boards representatives (Juntas Parroquiales), the community leaders, provincial board of the Intercultural bilingual education system, community based organizations, among others to: socialize the project objectives and define where to install the panels. |  | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A2 Improvement of the selected communities electrical devices to guarantee safety minimum standards |  |  |  | x | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A3 Delivery of the solar panels by the provider in the selected communities |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A4 Installation of solar panels by the provider in the selected communities |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A5 Select a group in each community and carry out a training process in solar panels management and maintenance by the provider. |  |  |  |  |  | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1. A6 To sign the delivery certificate that assure the legal transference of the solar panels property with the community representatives |  |  |  |  |  | x | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R.1.A7 To carry out a workshop in each community to raise awareness about the solar panel benefits and create a communitarian sense of ownership of this technological tool. |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |  |  |  |  |
| R.2. The quality of rural education has been improved by the use of pedagogical applications of ICTs in the classrooms and a training process in the use and maintenance of technological devices. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| R2.A1 To carry out a diagnosis report about the possible applications of ICTs in the educational field. |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |
| R2.A2 Meetings with local actors such as: the community leaders, provincial board of the Intercultural bilingual education system, in order to define the practical applications of ICTs to be implemented in the educational field based on the diagnosis report. |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |  |  |  |  |  |  |  |  |
| R2.A3 To provide rural schools of the selected communities with computers to improve their technological skills and introduce new teaching methodologies. |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x |  |  |  |  |  |  |  |
| R2.A4 To carry out a training process to the schools' teachers in the use and maintenance of computers, and in pedagogical methodologies based on ICTs applications. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x | x | x |  |  |  |  |
| R.2.A5. To systematize the experience and knowledge that the project has produced. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x |  |  |  |
| R.2.A6. To elaborate a communication plan in order to spread the experience and knowledge that the project has produced among local authorities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x |  |  |  |
| R.2.A7. To implement the communication plan among local authorities. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | x | x | x |

8. Development objectives and cross-cutting themes of the Project

| 8.1. What is/are the development objective(s) of the Project? Mark one main objective and max. 3 other significant objectives: |  |  |
| --- | --- | --- |
| Main objective | Other objective |  |
|  |  | Abolishing extreme poverty and famine |
|  |  | Extending elementary education to all |
|  |  | Improvement of gender equality and the situation of women |
|  |  | Diminishing infant mortality |
|  |  | Improving the health of pregnant women |
|  |  | Work against HIV/Aids |
|  |  | Work against malaria and other significant illnesses |
|  | X | Sustainable development of the environment |
|  |  | Access to clean water |
|  |  | Improving living conditions in the slums |
|  |  | Improving the working conditions of the private sector and increasing economic interaction |
|  |  | Advancing democracy, human rights and good governance |
|  |  | Advancing the state of peace and security |
|  |  | Developing a just and regulated international trade and financial system |
|  |  | Solving the debt problem of developing countries using national and international means |
| X |  | Bringing the benefits of using new technology and especially information technology to developing countries in co-operation with the private sector |
|  |  | None of the above. Other, explain. |

If the project support applied for is 20.000 € or more, please answer the following question:

8.2 How does the Project plan take into account the Poverty Reduction Strategy Paper (PRSP) or other equivalent national plans of the developing country concerned? If it has not been taken into account, please justify:

Over the past years, Ecuador has made strides in taking effective ownership of the Millennium Development Goals (MDGs) at both national and local levels. In 2005, the government affirmed that the MDGs were “state policy” and completed the first National MDG Report. Since then, the MDGs have taken their place in the public planning process (in the Social Agenda for 2006), in sectoral plans (the Ten-Year Plan for Education 2006-2015 and the Plan for Sustainable Tourism 2007-2020), and particularly at local government level. Ecuador’s new government, which came to power in January 2007, fully incorporated the MDGs in its agenda. The government is finalizing the Human National Development Plan 2007-2015, based on the MDGs. This Plan will have a regional focus and be extensively based on the localization work of the MDGs.

The proposed project between the Finnish Children and Youth Foundation and the Fundación Esquel will support the National Ten-Year Plan for Education by bringing solar power to rural schools, thus enabling the use of computers and other electric equipment in the instruction. Bilingual teachers will also be able to use internet for e-learning (professional program provided by the Ministry of Education).

The Project contributes mainly to the Millennium Development Goals numbers seven and eight, and to lesser extent to the goal number two.

| 8.3. Cross-cutting themes of development policy |  |  |
| --- | --- | --- |
| The development policy program of the Finnish government contains a number of cross-cutting themes that are to be taken into account in all development activities. |  |  |
| Instructions: In the column "impact" please mark a sign as advised below according to the impact this Project is estimated to have. Justify with one sentence the most important positive and negative impacts of the Project. |  |  |
| Options: |  |  |
|  | ++ | significant positive impact |
|  | + | positive impact |
|  | 0 | no impact |
|  | - | negative impact |
| Themes | Impact | Justification/Additional information |
| Impact on the Environment |  |  |
| Access to clean water and sanitation | 0 |  |
| Environmental distress (soil, water, atmosphere, waste) | 0 |  |
| Protection of biodiversity | 0 |  |
| Sustainable use of natural resources (incl. Energy, consumption, erosion) | ++ | The selected communities will count with solar energy in schools in order to have a constant energy supply to carry out educational activities. |
| Reducing gender inequality |  |  |
| Division of work between men and women | 0 |  |
| Women's access to income and their right to possess | + | The provision of new electrical devices and of a constant energy supply in the selected communities will benefit to the entire community, including men and women. |
| Women's participation in decision making | + | They would participate in reunion deciding the strategy of installation and management of the photovoltaic cells. |
| Sexual health and reproductive rights | 0 |  |
| Reducing violence | 0 |  |
| Equal opportunities to education | + | All the students, girls and boys, will benefit from a constant energy supply that will allow them to participate in more educational activities. |
| Supporting the most vulnerable groups (the disabled, ethnic or religious minorities, aboriginals, children) |  |  |
| The most vulnerable groups as members of the community (the attitudes towards the most vulnerable) | 0 |  |
| Empowerment of the most vulnerable groups | 0 |  |
| Equal rights of the most vulnerable groups | + | The project’s results will benefit to all the selected rural indigenous communities which are vulnerable groups in these provinces and in Ecuador. |
| Good governance and enhancing democracy |  |  |
| Reducing corruption | 0 |  |
| Strengthening the local skills on good governance | 0 |  |
| Transparency of financial management and information (among implementors) | 0 |  |
| Improving information exchange in the civil society | 0 |  |
| Improving involvement in the civil society | 0 |  |

9. Signatures

Place and date	Place and date

___________________________	___________________________

Eila Kauppinen	Pär Stenbäck
Executive Director	Chairman of the Board

Appendices

1 – Schools selection

[1] Functional illiteracy refers to the inability of an individual to use reading, writing, and (to an extent computational) skills efficiently in everyday life situations. Illiteracy is the inability to read or write simple sentences in any language.

http://www.olade.org.ec/ecuadorEn.html

Plan Maestro de Electrificación 2007-2016 – promoted by CONELEC, the National Council on Electricity and passed on December, 2007.

Corporación para Investigación Energética de Ecuador  - CIE http://www.energia.org.ec/index.html

The selection is made during the meeting with young people of the participating communities, activity 2.1